## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment Setup & Python Configuration | MUST HAVE | Python, Dask, Ray | Priyanka Sriram,Sneha | 3- Completed
S1 | S1 | US-002 | Log Schema Design & Pipeline Planning | MUST HAVE | Design Docs | Domesh,Srinithi | 3- Completed
S2 | S2 | US-003 | Log Ingestion Module Development | MUST HAVE | Python logging, Regex | Srinithi,Domesh | 3- Completed
S2 | S2 | US-004 | Distributed Processing using Dask/Ray | MUST HAVE | Dask, Ray | Priyanka Sriram,Sneha | 3- Completed
S3 | S3 | US-005 | Anomaly Detection (Statistical Models) | MUST HAVE | Z Score | Rakshitha | 2- In Progress
S3 | S3 | US-006 | Alert System Integration (Email/Slack) | SHOULD HAVE | SMTP, Slack API | Rakshitha | 2- In Progress
S4 | S4 | US-007 | Dashboard Development (Streamlit/Dash) | MUST HAVE | Streamlit, Plotly | Priyanka Sriram,Sneha,Rakshitha,Srinithi,Domesh | 1- Not Started
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 52 | 20 | 19 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project Introduction (Log Analytics Engine) | 2026-02-09 | 2026-02-10 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Others | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Environment Setup (Python, Dask, Ray) | 2026-02-11 | 2026-02-12 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Setup | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Log Schema Design & Planning | 2026-02-13 | 2026-02-14 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Design | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Log Ingestion Module Development | 2026-02-15 | 2026-02-18 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Coding | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Log Parsing using Regex & Python | 2026-02-19 | 2026-02-22 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Coding | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Distributed Processing using Dask | 2026-02-23 | 2026-02-26 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Coding | Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Distributed Processing using Ray | 2026-02-27 | 2026-03-03 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Coding | In Progress | 8 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Testing Log Processing Performance | 2026-03-04 | 2026-03-07 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Testing | In Progress | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Documentation of Ingestion & Processing | 2026-03-08 | 2026-03-11 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Documentation | In Progress | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Code Review & Optimization | 2026-03-12 | 2026-03-15 | Priyanka Sriram,Rakshitha,Sneha,Domesh,Srinithi | Review | In Progress | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project architecture | Discussed with mentor and reviewed project documentation
Sprint 1 | Day 4 | Difficulty in understanding Dask and Ray setup | Referred official documentation and practiced basic examples
Sprint 1 | Day 6 | Issues in configuring Python environment | Reinstalled dependencies and resolved version conflicts
Sprint 2 | Day 8 | Difficulty in designing log schema | Analyzed sample logs and finalized schema structure
Sprint 2 | Day 10 | Errors in log ingestion process | Debugged code and validated with test log files
Sprint 3 | Day 14 | Complexity in writing regex for parsing | Tested and refined regex patterns using online tools
Sprint 3 | Day 18 | Difficulty in implementing anomaly detection | Studied statistical methods and applied z-score technique
Sprint 4 | Day 22 | Issues in testing and validating results | Created test cases and compared outputs for accuracy

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team members name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-09 | 2026-02-15 | Priyanka Sriram,Rakshtha,Sneha,Domesh,Srinithi | Understanding project architecture and tools (Dask, Ray) | Assuming system design without validation | Participating in mentor discussions | Clarified architecture and finalized initial project workflow
2 | Sprint 2 | 2026-02-16 | 2026-02-22 | Priyanka Sriram,Rakshtha,Sneha,Domesh,Srinithi | Implementing log ingestion and parsing modules | Ignoring edge cases in log data | Writing clean and modular code | Successfully built ingestion module and tested with sample logs
3 | Sprint 3 | 2026-02-23 | 2026-03-01 | Priyanka Sriram,Rakshtha,Sneha,Domesh,Srinithi | Developing distributed processing using Dask/Ray | Running inefficient sequential code | Optimizing performance and debugging | Improved processing speed using parallel execution
4 | Sprint 4 | 2026-03-02 | 2026-03-08 | Priyanka Sriram,Rakshtha,Sneha,Domesh,Srinithi | Implementing anomaly detection techniques | Using unoptimized detection logic | Testing models with sample datasets | Applied statistical methods (z-score) for anomaly detection
5 | Sprint 5 | 2026-03-09 | 2026-03-15 | Priyanka Sriram,Rakshtha,Sneha,Domesh,Srinithi | Integrating modules and validating outputs | Skipping intermediate testing | Ensuring modular integration | Successfully integrated ingestion and detection modules
6 | Sprint 6 | 2026-03-16 | 2026-03-21 | Priyanka Sriram,Rakshtha,Sneha,Domesh,Srinithi | Performing system testing and debugging | Delaying bug fixes | Reviewing outputs and logs | Fixed identified issues and improved system stability
7 | Sprint 7 | 2026-03-22 | 2026-02-26 | Priyanka Sriram,Rakshtha,Sneha,Domesh,Srinithi | Finalizing documentation and preparing reports | Postponing documentation work | Maintaining code quality and structure | Completed final documentation and prepared project for submission